# Statement of Work

Self-Guided Audio Tour Infrastructure Solution

Prepared for: Museums In Europe

Prepared by: Ariel Eshkol

Date: January 12, 2026

# Document Control

| Document Title | Museums In Europe - Self-Guided Tours Infrastructure SOW |
| --- | --- |
| Version | 6.0 (Condensed with Diagrams) |
| Date | January 12, 2026 |
| Author | AllCloud Solutions Team |
| Client Contact | Ofer Gradus, CEO |
| Status | Draft for Review |

# Table of Contents

1. Executive Summary

2. Organization Overview

3. Critical Requirements & Solution Overview

4. User Experience Flows

5. Scope of Work & Roles/Responsibilities

6. Project Timeline & Deliverables

7. Pricing & Commercial Terms

# 1. Executive Summary

## 1.1 Project Overview

Museums In Europe seeks to implement a self-guided audio tour infrastructure for their Israel museum location. AllCloud proposes a WiFi-enabled, accuracy-focused AWS solution that provides personalized visitor experiences while maintaining strict historical accuracy controls.

Key Solution Components:

Content Management System (CMS) with curator approval workflows

AI-powered personalization engine (content selection only, NO fact generation)

RESTful API layer for frontend integration

Secure content repository with Israel data residency

Real-time content delivery via strong WiFi infrastructure

## 1.2 Critical Success Factors

| Factor | Requirement | AllCloud Solution |
| --- | --- | --- |
| **Historical Accuracy** | NO AI-generated facts | RAG + Curator approval + Bedrock Guardrails |
| **WiFi Performance** | Real-time content delivery | S3 caching + API Gateway + DynamoDB DAX |
| **Data Residency** | All data in Israel | il-central-1 region + LZA enforcement |
| **Clear Roles** | Defined responsibilities | AllCloud: Infrastructure/CMS; Partner: Frontend |

## 1.3 Project Scope

AllCloud Deliverables:

AWS infrastructure (multi-account LZA architecture)

Content Management System (backend + curator portal)

RESTful APIs for frontend integration

AI personalization engine (Amazon Bedrock)

Security, monitoring, and backup systems

Out of Scope (Frontend Partner):

Mobile application development (iOS/Android/Web)

User interface and UX design

QR code scanning functionality

Visitor-facing features

## 1.4 Investment Summary

| Item | Cost | Notes |
| --- | --- | --- |
| **Professional Services** | $70,000 | One-time implementation |
| **Monthly AWS Infrastructure** | $200-315/month | Israel region, serverless |
| **3-Year Total Cost of Ownership** | $77,200-81,340 | Services + infrastructure |

## 1.5 Timeline

Total Duration: 8-10 weeks from contract signature to production launch

| Phase | Duration | Key Deliverable |
| --- | --- | --- |
| Infrastructure Setup | 2 weeks | Operational AWS environment |
| CMS Development | 2-3 weeks | Operational CMS with APIs |
| Integration & Testing | 2-3 weeks | Integrated system |
| UAT & Launch | 1-2 weeks | Live production system |

# 2. Organization Overview

## 2.1 Client Profile

Organization: Museums In Europe

Project Sponsor: Ofer Gradus, CEO

Location: Israel

Project: Self-Guided Audio Tour Infrastructure

## 2.2 Current State

The museum currently lacks a digital infrastructure for self-guided audio tours. Visitors have no personalized experience, and content management is manual and fragmented.

Current Challenges:

No digital content delivery system

No personalization capabilities

Manual content management

No visitor analytics

Limited scalability

## 2.3 Desired Future State

A modern, WiFi-enabled infrastructure that delivers personalized audio tours to visitors while maintaining strict historical accuracy controls and curator oversight.

Key Objectives:

Personalized visitor experiences based on preferences

Real-time content delivery via strong WiFi

Curator-controlled content with approval workflows

AI-powered content selection (NOT generation)

Israel data residency compliance

Scalable, secure AWS infrastructure

# 3. Critical Requirements & Solution Overview

## 3.1 Critical Requirements

| Requirement | Description | AllCloud Solution |
| --- | --- | --- |
| **Historical Accuracy** | NO AI-generated facts; all content curator-approved | RAG approach + Bedrock Guardrails + Human approval gates + Audit trail |
| **WiFi-Enabled** | Real-time content delivery with strong WiFi | S3 caching + API Gateway caching + DynamoDB DAX + Optimized delivery |
| **Israel Data Residency** | All data must remain in Israel | il-central-1 region + LZA enforcement + No cross-border transfers |
| **Clear Roles** | Defined responsibilities between parties | See Roles & Responsibilities table (Section 5) |

## 3.2 Personalization Questionnaire (7 Parameters)

The system collects visitor preferences to generate personalized itineraries:

| Parameter | Options | Purpose |
| --- | --- | --- |
| **Language** | English, Hebrew, others | Content language selection |
| **Age Range** | Children, Teens, Adults, Seniors | Content complexity level |
| **Culture/Religion** | Dietary, observances, sensitivities | Content filtering |
| **Points of Interest** | Art periods, themes, collections | Content matching |
| **Gender** | Optional | Analytics and recommendations |
| **Visit Duration** | 30min - 4+ hours | Itinerary length |
| **Must-See Items** | Specific exhibits | Anchor points in itinerary |

## 3.3 Solution Architecture Overview

[See Diagram 1: LZA OU & Account Structure]

Figure 1: AWS Landing Zone Accelerator multi-account organizational structure with Security, Infrastructure, and Workloads OUs.

[See Diagram 2: Detailed Technical Architecture]

Figure 2: Complete AWS architecture showing VPCs, subnets, all AWS services, Transit Gateway hub-spoke topology, and security components in Israel region.

### Core Components

| Component | Technology | Purpose |
| --- | --- | --- |
| **Content Management** | S3 + DynamoDB + Cognito | Curator portal for content upload and approval |
| **API Layer** | API Gateway + Lambda | RESTful APIs for frontend integration |
| **Personalization Engine** | Amazon Bedrock (RAG) | AI content selection and itinerary generation |
| **Voice Generation** | Amazon Polly | Text-to-speech for approved content (Phase 1) |
| **Data Storage** | S3 + DynamoDB | Audio files, transcripts, metadata |
| **Caching** | S3 + DynamoDB DAX | Pre-generated audio by visitor profile |
| **Security** | WAF + KMS + CloudTrail | Access control, encryption, audit logging |
| **Monitoring** | CloudWatch + AWS Backup | Metrics, logs, automated backups |

### AWS Services Summary

| Service | Monthly Cost | Justification |
| --- | --- | --- |
| Lambda | $25-40 | Serverless compute, automatic scaling, pay-per-use |
| API Gateway | Included in Lambda | Managed RESTful APIs, built-in caching |
| S3 | $6-10 | 99.999999999% durability, versioning, lifecycle policies |
| DynamoDB | $15-25 | Single-digit ms latency, automatic scaling |
| DynamoDB DAX | Included | In-memory cache, microsecond latency |
| Bedrock | $15-25 | Grounded AI, RAG, no hallucination |
| Polly | $10-15 | Natural voice generation, multiple languages |
| CloudFront | $20-30 | Global CDN, edge caching |
| VPC/Networking | $85-130 | Transit Gateway, NAT, VPC endpoints |
| Security (WAF/KMS) | $16-23 | Web firewall, encryption key management |
| Monitoring | $20-35 | CloudWatch, CloudTrail, AWS Backup |
| **Total** | **$200-315** | **Serverless, auto-scaling, Israel region** |

# 4. User Experience Flows

## 4.1 Visitor Journey

[See Diagram 3: Visitor User Experience Flow]

Figure 3: Complete visitor journey from arrival through questionnaire, AI-powered itinerary generation, gallery experience with real-time content delivery, and exit.

### Visitor Journey Summary

| Step | Activity | Technology | Duration |
| --- | --- | --- | --- |
| **1. Arrival** | Receive device or download app via QR code | Frontend app | 2-3 min |
| **2. Questionnaire** | Answer 7 personalization questions | API Gateway + Lambda + DynamoDB | 3-5 min |
| **3. Itinerary** | AI generates personalized tour route | Bedrock + Lambda | 10-30 sec |
| **4. Gallery** | Scan QR codes, receive audio content | API Gateway + S3 + Polly | Real-time |
| **5. Exit** | Sync analytics, thank you message | CloudWatch + DynamoDB | 1 min |

Note: All technical details (API calls, AWS services, data flow) are shown in Diagram 3. The system leverages strong WiFi throughout the museum for real-time content delivery.

## 4.2 Museum Employee Workflow

[See Diagram 4: Museum Employee User Experience Flow]

Figure 4: Content creation workflow showing staff upload, AI voice generation (Amazon Polly), curator approval gates, and publication process with AWS service integration.

[DIAGRAM 4 PLACEHOLDER - Insert diagram here]

### Content Lifecycle Summary

| Role | Activity | System | Status |
| --- | --- | --- | --- |
| **Content Creator** | Upload text content + images | CMS Portal (S3 + CloudFront) | Draft |
| **System** | Auto-generate audio via Polly | Amazon Polly + Lambda | Pending Approval |
| **Curator** | Review content for accuracy | CMS Portal (Cognito auth) | Under Review |
| **Curator** | Approve or reject with comments | Lambda + Bedrock Guardrails | Approved/Rejected |
| **System** | Publish to production repository | S3 + DynamoDB + CloudWatch | Published |
| **AI** | Select content for visitor itineraries | Bedrock (RAG) | In Use |

Key Controls:

All content requires curator approval before publication

AI can only select from approved content (cannot generate facts)

Complete audit trail (author, approver, date, version)

Bedrock Guardrails prevent unauthorized content modifications

Content versioning and rollback capability

Note: All technical details (authentication, API calls, approval logic, AWS services) are shown in Diagram 4.

## 4.3 AI Usage Policy

### What AI WILL Do

✅ Analyze questionnaire responses to understand visitor profile

✅ Select which approved exhibits to recommend

✅ Generate personalized itinerary with optimal sequence

✅ Match visitor age group to appropriate content variants

✅ Suggest related exhibits based on interests

✅ Optimize route through museum based on time available

### What AI Will NOT Do

❌ Generate new historical facts or information

❌ Modify curator-approved content

❌ Create new audio narration (Polly generates from approved text only)

❌ Translate content without curator approval

❌ Answer visitor questions with generated responses

❌ Make up information not in approved content

### Amazon Bedrock Guardrails

Content filters prevent generation of new historical facts

Topic filters restrict AI to approved content only

Word filters block unauthorized modifications

Hallucination detection prevents fabricated information

Grounding check verifies all AI responses reference approved source content

Violations logged and alerted to security team

# 5. Scope of Work & Roles/Responsibilities

## 5.1 Roles & Responsibilities

| Component | AllCloud | Frontend Partner | Museum Staff |
| --- | --- | --- | --- |
| **AWS Infrastructure** | ✅ Design & implement | ❌ | ❌ |
| **LZA Multi-Account Setup** | ✅ Deploy & configure | ❌ | ❌ |
| **CMS Backend** | ✅ Build APIs & logic | ❌ | ❌ |
| **CMS Frontend (Curator Portal)** | ✅ Build web portal | ❌ | ❌ |
| **Mobile App** | ❌ | ✅ Develop (iOS/Android/Web) | ❌ |
| **QR Code Scanning** | ❌ | ✅ Implement | ❌ |
| **Audio Playback UI** | ❌ | ✅ Implement | ❌ |
| **Content Upload** | ✅ Provide APIs | ❌ | ✅ Upload via CMS |
| **Content Approval** | ✅ Workflow system | ❌ | ✅ Review & approve |
| **AI Voice Generation** | ✅ Polly integration | ❌ | ❌ |
| **API Documentation** | ✅ Provide specs | ✅ Consume APIs | ❌ |
| **Integration Testing** | ✅ Backend testing | ✅ Frontend testing | ✅ UAT |
| **Infrastructure Monitoring** | ✅ CloudWatch setup | ❌ | ❌ |
| **End-User Support** | ❌ | ✅ App support | ✅ Content support |
| **AWS Cost Management** | ✅ Optimize & monitor | ❌ | ✅ Budget approval |

## 5.2 AllCloud Deliverables

| Deliverable | Description | Timeline |
| --- | --- | --- |
| **AWS Infrastructure** | Multi-account LZA setup, VPCs, networking | Week 1-2 |
| **Content Management System** | Backend APIs + Curator portal | Week 3-5 |
| **AI Personalization Engine** | Bedrock integration, RAG setup | Week 4-5 |
| **Voice Generation** | Polly integration, audio pipeline | Week 4-5 |
| **Security & Monitoring** | WAF, KMS, CloudWatch, CloudTrail | Week 2-6 |
| **API Documentation** | OpenAPI specs, integration guide | Week 5-6 |
| **Testing & Validation** | Load testing, security testing | Week 7-8 |
| **Training** | CMS training for museum staff | Week 8 |
| **Production Launch** | Go-live support | Week 8-10 |

## 5.3 Frontend Partner Deliverables (NOT AllCloud)

| Deliverable | Description | Notes |
| --- | --- | --- |
| **Mobile App** | iOS/Android/Web application | AllCloud provides APIs only |
| **UI/UX Design** | Visitor-facing interface | AllCloud provides recommendations |
| **QR Code Scanner** | Exhibit code scanning | AllCloud provides exhibit IDs |
| **Offline Caching** | Local content storage | AllCloud provides caching strategy |
| **Audio Player** | Playback controls | AllCloud provides audio files |
| **App Store Submission** | iOS/Android deployment | AllCloud not involved |
| **End-User Support** | Visitor troubleshooting | AllCloud supports infrastructure only |

## 5.4 Museum Staff Responsibilities

| Responsibility | Description | Support from AllCloud |
| --- | --- | --- |
| **Content Creation** | Write exhibit descriptions, record audio | CMS portal provided |
| **Content Approval** | Review and approve all content | Approval workflow provided |
| **Content Management** | Organize exhibitions and exhibits | Hierarchical CMS provided |
| **User Acceptance Testing** | Validate system meets requirements | Testing support provided |
| **Budget Approval** | Approve AWS infrastructure costs | Cost monitoring provided |
| **Staff Training** | Learn CMS portal usage | Training sessions provided |

## 5.5 Integration Points

| Integration | AllCloud Provides | Frontend Partner Consumes |
| --- | --- | --- |
| **Questionnaire API** | POST /api/questionnaire/submit | Submit visitor preferences |
| **Itinerary API** | POST /api/itinerary/generate | Get personalized tour |
| **Content API** | GET /api/content/{exhibitId} | Retrieve audio + metadata |
| **Recommendations API** | POST /api/recommendations/next | Get next exhibit suggestion |
| **Analytics API** | POST /api/analytics/sync | Send usage data |
| **Authentication** | OAuth 2.0 / API keys | Secure API access |

API Documentation: AllCloud will provide complete OpenAPI specifications, example requests/responses, and integration guide.

# 6. Project Timeline & Deliverables

## 6.1 Project Timeline

Total Duration: 8-10 weeks from contract signature to production launch

| Phase | Duration | Key Activities | Deliverables | Dependencies |
| --- | --- | --- | --- | --- |
| **Phase 1: Infrastructure** | 2 weeks | AWS account setup, LZA deployment, VPC configuration, Transit Gateway, security baseline | Operational AWS environment, network connectivity, security controls | Contract signature, AWS account access |
| **Phase 2: CMS Development** | 2-3 weeks | Backend APIs, curator portal, content upload, approval workflows, Polly integration | Operational CMS with APIs, curator portal, API documentation | Phase 1 complete |
| **Phase 3: Integration** | 2-3 weeks | Frontend integration, API testing, Bedrock setup, end-to-end testing | Integrated system, tested APIs, personalization engine | Phase 2 complete, frontend partner ready |
| **Phase 4: Testing & UAT** | 1-2 weeks | Load testing, security testing, UAT with museum staff, bug fixes | Test reports, UAT sign-off, production-ready system | Phase 3 complete, test content available |
| **Phase 5: Launch** | 1 week | Production deployment, monitoring setup, staff training, go-live support | Live production system, trained staff, operational runbooks | Phase 4 complete, UAT approved |

## 6.2 Milestones

| Milestone | Target Week | Success Criteria |
| --- | --- | --- |
| **M1: Infrastructure Ready** | Week 2 | AWS accounts operational, VPCs configured, security baseline deployed |
| **M2: CMS Operational** | Week 5 | Curator portal live, APIs functional, content upload working |
| **M3: Integration Complete** | Week 7 | Frontend integrated, APIs tested, personalization working |
| **M4: UAT Approved** | Week 8 | Museum staff sign-off, all test cases passed |
| **M5: Production Launch** | Week 10 | System live, visitors using app, monitoring active |

## 6.3 Detailed Deliverables

### Infrastructure Deliverables

| Deliverable | Description | Format |
| --- | --- | --- |
| **AWS Account Structure** | LZA multi-account setup (Management, Security, Infrastructure, Workloads) | AWS Organizations |
| **Network Architecture** | VPCs, subnets, Transit Gateway, NAT, Internet Gateway | Terraform/CDK code |
| **Security Baseline** | WAF, KMS, Security Groups, NACLs, IAM roles | Terraform/CDK code |
| **Monitoring Setup** | CloudWatch dashboards, alarms, CloudTrail, AWS Backup | AWS Console + IaC |
| **Infrastructure Documentation** | Architecture diagrams, network topology, security controls | PDF + Diagrams |

### Application Deliverables

| Deliverable | Description | Format |
| --- | --- | --- |
| **CMS Backend** | RESTful APIs for content management, approval workflows | Lambda + API Gateway |
| **Curator Portal** | Web application for content upload and approval | S3 + CloudFront |
| **Personalization Engine** | Bedrock integration, RAG setup, itinerary generation | Lambda + Bedrock |
| **Voice Generation** | Polly integration, audio pipeline, multi-language support | Lambda + Polly |
| **API Documentation** | OpenAPI specs, integration guide, example code | Markdown + OpenAPI YAML |

### Testing Deliverables

| Deliverable | Description | Format |
| --- | --- | --- |
| **Test Plan** | Test strategy, test cases, acceptance criteria | PDF |
| **Load Test Results** | Performance metrics, scalability validation | PDF + Screenshots |
| **Security Test Results** | Vulnerability scan, penetration test findings | PDF (confidential) |
| **UAT Sign-Off** | Museum staff approval, test case results | Signed document |

### Training & Support Deliverables

| Deliverable | Description | Format |
| --- | --- | --- |
| **CMS User Guide** | Step-by-step guide for content creators and curators | PDF + Video |
| **Training Sessions** | Live training for museum staff (2 sessions) | Virtual/On-site |
| **Operational Runbooks** | Incident response, troubleshooting, maintenance | PDF |
| **Go-Live Support** | 2 weeks of dedicated support post-launch | Email + Slack |

## 6.4 Dependencies & Assumptions

### Dependencies

| Dependency | Owner | Impact if Delayed |
| --- | --- | --- |
| **AWS Account Access** | Museum IT | Cannot start infrastructure setup |
| **Frontend Partner Readiness** | Frontend Partner | Cannot complete integration testing |
| **Test Content** | Museum Staff | Cannot perform UAT |
| **Budget Approval** | Museum Finance | Cannot deploy production resources |
| **Staff Availability for Training** | Museum HR | Cannot complete training |

### Assumptions

| Assumption | Risk if Invalid |
| --- | --- |
| Strong WiFi available throughout museum | May need offline caching strategy |
| Museum staff available for UAT | UAT phase may extend |
| Frontend partner has API integration experience | May need additional integration support |
| Content available in digital format | May need content digitization phase |
| AWS Israel region (il-central-1) available | May need alternative region strategy |

# 7. Pricing & Commercial Terms

## 7.1 Professional Services Pricing

| Service Category | Cost | Description |
| --- | --- | --- |
| **Infrastructure Setup** | $15,000 | AWS account setup, LZA deployment, VPC configuration, security baseline |
| **CMS Development** | $30,000 | Backend APIs, curator portal, content management, approval workflows |
| **AI Integration** | $15,000 | Bedrock setup, RAG configuration, Polly integration, personalization engine |
| **Testing & Validation** | $5,000 | Load testing, security testing, UAT support |
| **Training & Documentation** | $5,000 | CMS training, API documentation, operational runbooks |
| **Total Professional Services** | **$70,000** | **One-time implementation cost** |

## 7.2 AWS Infrastructure Costs

### Monthly Cost Breakdown

| Service Category | Monthly Cost | % of Total | Notes |
| --- | --- | --- | --- |
| **Compute (Lambda)** | $25-40 | 10-13% | Serverless, pay-per-use, automatic scaling |
| **Storage (S3)** | $6-10 | 2-3% | Audio files, images, backups |
| **Database (DynamoDB)** | $15-25 | 5-8% | Metadata, profiles, on-demand pricing |
| **AI/ML (Bedrock, Polly)** | $25-40 | 8-13% | Content selection, voice generation |
| **Networking (VPC, TGW, NAT)** | $85-130 | 28-41% | Transit Gateway, NAT Gateway, VPC endpoints |
| **Security (WAF, KMS)** | $16-23 | 5-7% | Web firewall, encryption |
| **Monitoring (CloudWatch, Backup)** | $20-35 | 6-11% | Logs, metrics, automated backups |
| **CDN (CloudFront)** | $20-30 | 7-10% | Global content delivery |
| **Total Monthly** | **$200-315** | **100%** | **Israel region, serverless architecture** |

Note: Costs based on estimated usage (5,000 visitors/month, 100 exhibits, 3 languages). Actual costs may vary based on usage patterns.

### Annual Cost Projection

| Year | Professional Services | AWS Infrastructure | Total |
| --- | --- | --- | --- |
| **Year 1** | $70,000 | $2,400-3,780 | $72,400-73,780 |
| **Year 2** | $0 | $2,400-3,780 | $2,400-3,780 |
| **Year 3** | $0 | $2,400-3,780 | $2,400-3,780 |
| **3-Year TCO** | **$70,000** | **$7,200-11,340** | **$77,200-81,340** |

## 7.3 Payment Terms

| Milestone | Payment | Deliverable |
| --- | --- | --- |
| **Contract Signature** | 30% ($21,000) | Project kickoff, AWS account setup begins |
| **Infrastructure Complete** | 20% ($14,000) | Operational AWS environment (Week 2) |
| **CMS Operational** | 30% ($21,000) | Functional CMS with APIs (Week 5) |
| **UAT Approved** | 15% ($10,500) | UAT sign-off (Week 8) |
| **Production Launch** | 5% ($3,500) | Go-live (Week 10) |
| **Total** | **100% ($70,000)** | **Complete implementation** |

AWS Infrastructure Costs: Billed monthly by AWS directly to client's AWS account. AllCloud provides cost monitoring and optimization recommendations.

## 7.4 Commercial Terms

### Warranty & Support

| Term | Details |
| --- | --- |
| **Warranty Period** | 90 days from production launch |
| **Warranty Coverage** | Bug fixes, performance issues, security vulnerabilities |
| **Response Time** | Critical: 4 hours; High: 8 hours; Medium: 24 hours; Low: 48 hours |
| **Go-Live Support** | 2 weeks of dedicated support post-launch (included) |

### Post-Warranty Support (Optional)

| Support Tier | Monthly Cost | Coverage |
| --- | --- | --- |
| **Basic** | $2,000/month | Email support, 48-hour response, business hours |
| **Standard** | $4,000/month | Email + phone, 8-hour response, extended hours |
| **Premium** | $8,000/month | 24/7 support, 2-hour response, dedicated engineer |

### Change Requests

| Type | Rate | Notes |
| --- | --- | --- |
| **Minor Changes** | Included | Small configuration changes, bug fixes |
| **Feature Enhancements** | $150/hour | New features, significant changes |
| **Emergency Changes** | $200/hour | After-hours, urgent changes |

### Assumptions & Exclusions

Included:

✅ AWS infrastructure design and implementation

✅ CMS backend and curator portal

✅ AI personalization engine

✅ API documentation and integration guide

✅ Training for museum staff

✅ 90-day warranty

Excluded:

❌ Mobile app development (frontend partner responsibility)

❌ Content creation or digitization

❌ On-premise hardware or networking

❌ Third-party software licenses

❌ Post-warranty support (optional, see above)

❌ Travel expenses (if on-site visits required)

## 7.5 Success Criteria & KPIs

| KPI | Target | Measurement |
| --- | --- | --- |
| **System Availability** | 99.9% uptime | CloudWatch monitoring |
| **API Response Time** | < 200ms (p95) | API Gateway metrics |
| **Content Delivery** | < 2 seconds | CloudFront + S3 metrics |
| **Curator Approval Time** | < 24 hours | CMS workflow metrics |
| **Visitor Satisfaction** | > 4.0/5.0 | Post-visit survey |
| **Historical Accuracy** | 100% curator-approved | Audit trail verification |
| **Data Residency** | 100% Israel region | AWS Config compliance |

## 7.6 Governance & Communication

| Activity | Frequency | Participants |
| --- | --- | --- |
| **Project Kickoff** | Once | AllCloud team, Museum stakeholders, Frontend partner |
| **Weekly Status Meetings** | Weekly | Project managers, technical leads |
| **Sprint Reviews** | Bi-weekly | Development team, Museum stakeholders |
| **Steering Committee** | Monthly | Executives, project sponsors |
| **Go-Live Readiness Review** | Once (Week 8) | All stakeholders |

Communication Channels:

Email: Daily updates, documentation

Slack: Real-time collaboration

Video Calls: Weekly meetings, reviews

Project Management Tool: Jira or equivalent

## 7.7 Terms & Conditions

### Intellectual Property

AllCloud retains IP rights to reusable components and frameworks

Museum owns all custom code and configurations specific to this project

Museum owns all content uploaded to the system

### Confidentiality

Both parties agree to maintain confidentiality of proprietary information

Non-disclosure agreement (NDA) required before project start

### Liability

AllCloud liability limited to professional services fees paid

Museum responsible for content accuracy and legal compliance

AWS infrastructure subject to AWS Service Level Agreements

### Termination

Either party may terminate with 30 days written notice

Museum pays for work completed to date

AllCloud provides knowledge transfer and documentation

### Acceptance

UAT sign-off required for final payment

Museum has 10 business days to review and approve deliverables

Issues must be documented and communicated within acceptance period